## Action_Plan_Summary (2) (hidden)
Column1 | Column2
Phase,Action,Description,Estimated Time,Files Affected
Phase 1 | Immediate (Day 1),Remove SMB Dependencies,"Remove smb2 package and all SMB-related code",4 hours,"package.json, file.controller.js"
Phase 1 | Immediate (Day 1),Simplify Storage Configuration,"Set BASE_PATH to local uploads folder, remove USE_SMB logic",2 hours,file.controller.js
Phase 1 | Immediate (Day 1),Clean Core Functions,"Remove SMB logic from uploadFile, getRawFile, deleteFile, renameFile",4 hours,file.controller.js
Phase 2 | Core Functionality (Day 2),Fix Folder Operations,"Clean getAvailableFolders, getFilesInFolder, createFolder functions",3 hours,file.controller.js
Phase 2 | Core Functionality (Day 2),Simplify Resumable Uploads,"Remove SMB logic from resumable upload system",3 hours,file.controller.js
Phase 2 | Core Functionality (Day 2),Test Basic Operations,"Manual testing of upload, download, folder creation",2 hours,All file operations
Phase 3 | Security & Features (Day 3),Strengthen Security,"Improve path traversal protection, add file type validation",4 hours,file.controller.js
Phase 3 | Security & Features (Day 3),Add Admin Features,"Create admin endpoints for client folder management",4 hours,file.controller.js
Phase 4 | Testing & Polish (Day 4),Comprehensive Testing,"Test all file operations, permissions, edge cases",4 hours,Manual testing
Phase 4 | Testing & Polish (Day 4),Error Handling,"Improve error messages and logging",2 hours,file.controller.js
Phase 4 | Testing & Polish (Day 4),Documentation,"Update comments, create basic API docs",2 hours,Multiple files
Phase 5 | MVP Verification (Day 5),End-to-End Testing,"Verify all MVP requirements work correctly",4 hours,Full application
Phase 5 | MVP Verification (Day 5),Performance Testing,"Test with larger files and multiple users",2 hours,Full application
Phase 5 | MVP Verification (Day 5),Final Cleanup,"Remove unused code, update environment config",2 hours,Multiple files
Total Estimated Time | 42 hours (approximately 5 working days)
Critical Path Items (Must be done first)
1. Remove SMB dependencies and code
2. Simplify storage configuration
3. Clean core file operation functions
4. Test basic upload/download functionality
MVP Requirements Verification
✓ Client can upload files to their folder
✓ Client can organize files in subfolders
✓ Client can download their files
✓ Admin can see all client folders
✓ Basic file management (rename, delete, create folders)
Immediate Next Steps
1. Backup current file.controller.js
2. Remove SMB2 package | npm uninstall smb2
3. Remove lines 6-22 (SMB initialization)
4. Remove lines 180-225 (SMB helper functions)
5. Set BASE_PATH = path.join(__dirname, '../../uploads')
6. Test basic upload functionality

## Action_Plan_Summary
Column1 | Column2
Phase,Action,Description,Estimated Time,Files Affected
Phase 1 | Immediate (Day 1),Remove SMB Dependencies,"Remove smb2 package and all SMB-related code",4 hours,"package.json, file.controller.js"
Phase 1 | Immediate (Day 1),Simplify Storage Configuration,"Set BASE_PATH to local uploads folder, remove USE_SMB logic",2 hours,file.controller.js
Phase 1 | Immediate (Day 1),Clean Core Functions,"Remove SMB logic from uploadFile, getRawFile, deleteFile, renameFile",4 hours,file.controller.js
Phase 2 | Core Functionality (Day 2),Fix Folder Operations,"Clean getAvailableFolders, getFilesInFolder, createFolder functions",3 hours,file.controller.js
Phase 2 | Core Functionality (Day 2),Simplify Resumable Uploads,"Remove SMB logic from resumable upload system",3 hours,file.controller.js
Phase 2 | Core Functionality (Day 2),Test Basic Operations,"Manual testing of upload, download, folder creation",2 hours,All file operations
Phase 3 | Security & Features (Day 3),Strengthen Security,"Improve path traversal protection, add file type validation",4 hours,file.controller.js
Phase 3 | Security & Features (Day 3),Add Admin Features,"Create admin endpoints for client folder management",4 hours,file.controller.js
Phase 4 | Testing & Polish (Day 4),Comprehensive Testing,"Test all file operations, permissions, edge cases",4 hours,Manual testing
Phase 4 | Testing & Polish (Day 4),Error Handling,"Improve error messages and logging",2 hours,file.controller.js
Phase 4 | Testing & Polish (Day 4),Documentation,"Update comments, create basic API docs",2 hours,Multiple files
Phase 5 | MVP Verification (Day 5),End-to-End Testing,"Verify all MVP requirements work correctly",4 hours,Full application
Phase 5 | MVP Verification (Day 5),Performance Testing,"Test with larger files and multiple users",2 hours,Full application
Phase 5 | MVP Verification (Day 5),Final Cleanup,"Remove unused code, update environment config",2 hours,Multiple files
Total Estimated Time | 42 hours (approximately 5 working days)
Critical Path Items (Must be done first)
1. Remove SMB dependencies and code
2. Simplify storage configuration
3. Clean core file operation functions
4. Test basic upload/download functionality
MVP Requirements Verification
✓ Client can upload files to their folder
✓ Client can organize files in subfolders
✓ Client can download their files
✓ Admin can see all client folders
✓ Basic file management (rename, delete, create folders)
Immediate Next Steps
1. Backup current file.controller.js
2. Remove SMB2 package | npm uninstall smb2
3. Remove lines 6-22 (SMB initialization)
4. Remove lines 180-225 (SMB helper functions)
5. Set BASE_PATH = path.join(__dirname, '../../uploads')
6. Test basic upload functionality

## MVP_Tasks_Detailed (2) (hidden)
Priority | Category | Task | Description | File Location | Lines | Status | Estimated Hours | Dependencies | Notes
1 | Core Refactoring | Remove SMB Package | Remove smb2 from package.json dependencies | backend_webbone/package.json |  | Not Started | 5 |  | npm uninstall smb2
1 | Core Refactoring | Remove SMB Environment Variables | Remove SMB_SHARE, SMB_DOMAIN, SMB_USERNAME, SMB_PASSWORD from .env | .env file |  | Not Started | 5 |  | Keep only CLIENT_FILES_BASE_PATH
1 | Core Refactoring | Remove SMB Import and Initialization | Remove SMB2 require and client initialization | backend_webbone/src/controllers/file.controller.js | 6-22 | Not Started | 1 |  | Lines 6-22 contain USE_SMB logic
1 | Core Refactoring | Remove SMB Helper Functions | Remove all smbReaddir, smbWriteFile, etc. functions | backend_webbone/src/controllers/file.controller.js | 180-225 | Not Started | 2 |  | Functions starting around line 180
1 | Core Refactoring | Simplify BASE_PATH | Set BASE_PATH to path.join(__dirname, '../../uploads') | backend_webbone/src/controllers/file.controller.js | 24 | Not Started | 5 |  | Replace env variable logic
1 | Core Refactoring | Remove smbJoin Helper | Remove smbJoin function completely | backend_webbone/src/controllers/file.controller.js | 26 | Not Started | 5 |  | No longer needed for local paths
1 | Core Refactoring | Simplify Multer Storage | Remove conditional USE_SMB logic from storage config | backend_webbone/src/controllers/file.controller.js | 28-40 | Not Started | 1 |  | Keep only diskStorage configuration
2 | Function Cleanup | Clean uploadFile Function | Remove SMB upload logic, keep only local file handling | backend_webbone/src/controllers/file.controller.js | 460-500 | Not Started | 2 | Core Refactoring | Remove USE_SMB checks
2 | Function Cleanup | Clean getFilesInFolder Function | Remove SMB readdir logic, use only fs.readdir | backend_webbone/src/controllers/file.controller.js | 350-380 | Not Started | 1 | Core Refactoring | Simplify to local filesystem only
2 | Function Cleanup | Clean getRawFile Function | Remove SMB file reading, keep only fs.createReadStream | backend_webbone/src/controllers/file.controller.js | 385-445 | Not Started | 2 | Core Refactoring | Critical for file downloads
2 | Function Cleanup | Clean createFolder Function | Remove SMB mkdir logic, use only fs.mkdir | backend_webbone/src/controllers/file.controller.js | 445-470 | Not Started | 1 | Core Refactoring | Folder creation functionality
2 | Function Cleanup | Clean deleteFile Function | Remove SMB unlink logic, use only fs.unlink | backend_webbone/src/controllers/file.controller.js | 295-325 | Not Started | 1 | Core Refactoring | File deletion functionality
2 | Function Cleanup | Clean renameFile Function | Remove SMB rename logic, use only fs.rename | backend_webbone/src/controllers/file.controller.js | 265-295 | Not Started | 1 | Core Refactoring | File rename functionality
2 | Function Cleanup | Clean getAvailableFolders Function | Remove SMB directory listing, use only fs.readdir | backend_webbone/src/controllers/file.controller.js | 330-365 | Not Started | 2 | Core Refactoring | Critical for folder navigation
2 | Function Cleanup | Fix completeResumable Function | Remove SMB write logic from resumable upload completion | backend_webbone/src/controllers/file.controller.js | 140-160 | Not Started | 2 | Core Refactoring | Large file upload completion
3 | New Features | Add Admin Client Folder Management | Create endpoints for admin to create new client folders | backend_webbone/src/controllers/file.controller.js |  | Not Started | 4 | Function Cleanup | New controller methods needed
3 | New Features | Add Admin Folder Deletion | Allow admin to delete client folders and all contents | backend_webbone/src/controllers/file.controller.js |  | Not Started | 3 | Admin Client Folder Management | Recursive deletion with safety checks
3 | New Features | Add Client Folder Initialization | Auto-create client folder structure on user creation | backend_webbone/src/controllers/user.controller.js |  | Not Started | 2 | Function Cleanup | Link with user management
3 | Security | Strengthen Path Traversal Protection | Improve path validation in all file operations | backend_webbone/src/controllers/file.controller.js | 385-445 | Not Started | 3 | Function Cleanup | Critical security issue
3 | Security | Add File Type Validation | Implement whitelist of allowed file extensions | backend_webbone/src/controllers/file.controller.js | 460-500 | Not Started | 2 | Function Cleanup | Security and storage management
3 | Security | Add File Size Limits | Implement per-client storage quotas | backend_webbone/src/controllers/file.controller.js | 460-500 | Not Started | 3 | Function Cleanup | Resource management
3 | Security | Add Rate Limiting for Uploads | Prevent upload spam and abuse | backend_webbone/src/middlewares/ |  | Not Started | 3 | Function Cleanup | New middleware needed
4 | Testing | Test Basic File Upload | Manual testing of single file upload |  |  | Not Started | 2 | Function Cleanup | Core functionality verification
4 | Testing | Test Resumable Upload System | Test chunked upload for large files |  |  | Not Started | 3 | Function Cleanup | Critical for large files
4 | Testing | Test Folder Operations | Test create, navigate, rename, delete operations |  |  | Not Started | 2 | Function Cleanup | File management verification
4 | Testing | Test Admin Permissions | Verify admin can access all client folders |  |  | Not Started | 2 | New Features | Permission system verification
4 | Testing | Test Client Isolation | Verify clients cannot access other client folders |  |  | Not Started | 2 | Security | Security verification
4 | Testing | Test File Download and Streaming | Verify file serving works correctly |  |  | Not Started | 2 | Function Cleanup | Core functionality
4 | Environment | Update Environment Configuration | Remove SMB variables, document LOCAL_FILES_BASE_PATH | .env |  | Not Started | 1 | Core Refactoring | Environment cleanup
4 | Environment | Create uploads Directory | Ensure backend_webbone/uploads directory exists | backend_webbone/uploads |  | Not Started | 5 |  | Directory structure
4 | Environment | Verify Route Configuration | Check that file routes are properly mounted | backend_webbone/src/app.js |  | Not Started | 1 |  | Route verification
5 | Error Handling | Improve Error Messages | Make all error responses user-friendly | backend_webbone/src/controllers/file.controller.js |  | Not Started | 2 | Function Cleanup | User experience
5 | Error Handling | Add Comprehensive Logging | Add debug logging for all file operations | backend_webbone/src/controllers/file.controller.js |  | Not Started | 2 | Function Cleanup | Development and debugging
5 | Error Handling | Handle Edge Cases | Add proper error handling for disk full, permissions, etc | backend_webbone/src/controllers/file.controller.js |  | Not Started | 3 | Function Cleanup | Production readiness
6 | MVP Verification | Client File Upload Works | Verify clients can upload files to their folder |  |  | Not Started | 1 | Testing | Core MVP requirement
6 | MVP Verification | Client Folder Organization Works | Verify clients can create and manage subfolders |  |  | Not Started | 1 | Testing | Core MVP requirement
6 | MVP Verification | Client File Download Works | Verify clients can download their files |  |  | Not Started | 1 | Testing | Core MVP requirement
6 | MVP Verification | Admin Folder Management Works | Verify admin can see and manage all client folders |  |  | Not Started | 1 | Testing | Admin MVP requirement
6 | MVP Verification | File Operations Work | Verify rename, delete, create folder operations |  |  | Not Started | 1 | Testing | Core MVP requirement
7 | Cleanup | Remove Unused Imports | Remove SMB2 and related unused imports | backend_webbone/src/controllers/file.controller.js | 1-5 | Not Started | 5 | Core Refactoring | Code cleanup
7 | Cleanup | Remove SMB Constants | Remove SMB_SINGLE_UPLOAD_LIMIT and other SMB constants | backend_webbone/src/controllers/file.controller.js | 42 | Not Started | 5 | Core Refactoring | Code cleanup
7 | Cleanup | Update Code Comments | Update comments to reflect local-only storage | backend_webbone/src/controllers/file.controller.js |  | Not Started | 1 | Function Cleanup | Documentation
7 | Cleanup | Remove writeWithTimeout Function | Remove or simplify timeout wrapper (may not be needed for local FS) | backend_webbone/src/controllers/file.controller.js | 200-220 | Not Started | 1 | Function Cleanup | Simplification
8 | Documentation | Update README | Document the simplified file storage system | README.md |  | Not Started | 2 | MVP Verification | Project documentation
8 | Documentation | Document API Endpoints | Create or update API documentation for file operations | docs/ |  | Not Started | 3 | MVP Verification | API documentation
8 | Documentation | Environment Setup Guide | Document environment variables and setup | docs/ |  | Not Started | 1 | Environment | Setup documentation