## MVP_Tasks_Detailed
Priority | Category | Task | Description | File Location | Lines | Status | Estimated Hours | Dependencies | Notes
1 | Core Refactoring | Remove SMB Package | Remove smb2 from package.json dependencies | backend_webbone/package.json |  | Done | 5 |  | npm uninstall smb2
1 | Core Refactoring | Remove SMB Environment Variables | Remove SMB_SHARE, SMB_DOMAIN, SMB_USERNAME, SMB_PASSWORD from .env | .env file |  | Done | 5 |  | Keep only CLIENT_FILES_BASE_PATH
1 | Core Refactoring | Remove SMB Import and Initialization | Remove SMB2 require and client initialization | backend_webbone/src/controllers/file.controller.js | 6-22 | Done | 1 |  | Lines 6-22 contain USE_SMB logic
1 | Core Refactoring | Remove SMB Helper Functions | Remove all smbReaddir, smbWriteFile, etc. functions | backend_webbone/src/controllers/file.controller.js | 180-225 | Done | 2 |  | Functions starting around line 180
1 | Core Refactoring | Simplify BASE_PATH | Set BASE_PATH to path.join(__dirname, '../../uploads') | backend_webbone/src/controllers/file.controller.js | 24 | Done | 5 |  | Replace env variable logic
1 | Core Refactoring | Remove smbJoin Helper | Remove smbJoin function completely | backend_webbone/src/controllers/file.controller.js | 26 | Done | 5 |  | No longer needed for local paths
1 | Core Refactoring | Simplify Multer Storage | Remove conditional USE_SMB logic from storage config | backend_webbone/src/controllers/file.controller.js | 28-40 | Done | 1 |  | Keep only diskStorage configuration
2 | Function Cleanup | Clean uploadFile Function | Remove SMB upload logic, keep only local file handling | backend_webbone/src/controllers/file.controller.js | 460-500 | Done | 2 | Core Refactoring | Remove USE_SMB checks
2 | Function Cleanup | Clean getFilesInFolder Function | Remove SMB readdir logic, use only fs.readdir | backend_webbone/src/controllers/file.controller.js | 350-380 | Done | 1 | Core Refactoring | Simplify to local filesystem only
2 | Function Cleanup | Clean getRawFile Function | Remove SMB file reading, keep only fs.createReadStream | backend_webbone/src/controllers/file.controller.js | 385-445 | Done | 2 | Core Refactoring | Critical for file downloads
2 | Function Cleanup | Clean createFolder Function | Remove SMB mkdir logic, use only fs.mkdir | backend_webbone/src/controllers/file.controller.js | 445-470 | Done | 1 | Core Refactoring | Folder creation functionality
2 | Function Cleanup | Clean deleteFile Function | Remove SMB unlink logic, use only fs.unlink | backend_webbone/src/controllers/file.controller.js | 295-325 | Done | 1 | Core Refactoring | File deletion functionality
2 | Function Cleanup | Clean renameFile Function | Remove SMB rename logic, use only fs.rename | backend_webbone/src/controllers/file.controller.js | 265-295 | Done | 1 | Core Refactoring | File rename functionality
2 | Function Cleanup | Clean getAvailableFolders Function | Remove SMB directory listing, use only fs.readdir | backend_webbone/src/controllers/file.controller.js | 330-365 | Done | 2 | Core Refactoring | Critical for folder navigation
2 | Function Cleanup | Fix completeResumable Function | Remove SMB write logic from resumable upload completion | backend_webbone/src/controllers/file.controller.js | 140-160 | Done | 2 | Core Refactoring | Large file upload completion
3 | New Features | Add Admin Client Folder Management | Create endpoints for admin to create new client folders | backend_webbone/src/controllers/file.controller.js |  | Done | 4 | Function Cleanup | New controller methods needed
3 | New Features | Add Admin Folder Deletion | Allow admin to delete client folders and all contents | backend_webbone/src/controllers/file.controller.js |  | In progress | 3 | Admin Client Folder Management | Recursive deletion with safety checks
3 | New Features | Add Client Folder Initialization | Auto-create client folder structure on user creation | backend_webbone/src/controllers/user.controller.js |  | Not Started | 2 | Function Cleanup | Link with user management
3 | Security | Strengthen Path Traversal Protection | Improve path validation in all file operations | backend_webbone/src/controllers/file.controller.js | 385-445 | Not Started | 3 | Function Cleanup | Critical security issue
3 | Security | Add File Type Validation | Implement whitelist of allowed file extensions | backend_webbone/src/controllers/file.controller.js | 460-500 | Not Started | 2 | Function Cleanup | Security and storage management
3 | Security | Add File Size Limits | Implement per-client storage quotas | backend_webbone/src/controllers/file.controller.js | 460-500 | Not Started | 3 | Function Cleanup | Resource management
3 | Security | Add Rate Limiting for Uploads | Prevent upload spam and abuse | backend_webbone/src/middlewares/ |  | Not Started | 3 | Function Cleanup | New middleware needed
4 | Testing | Test Basic File Upload | Manual testing of single file upload |  |  | Not Started | 2 | Function Cleanup | Core functionality verification
4 | Testing | Test Resumable Upload System | Test chunked upload for large files |  |  | Not Started | 3 | Function Cleanup | Critical for large files
4 | Testing | Test Folder Operations | Test create, navigate, rename, delete operations |  |  | Not Started | 2 | Function Cleanup | File management verification
4 | Testing | Test Admin Permissions | Verify admin can access all client folders |  |  | Not Started | 2 | New Features | Permission system verification
4 | Testing | Test Client Isolation | Verify clients cannot access other client folders |  |  | Not Started | 2 | Security | Security verification
4 | Testing | Test File Download and Streaming | Verify file serving works correctly |  |  | Not Started | 2 | Function Cleanup | Core functionality
4 | Environment | Update Environment Configuration | Remove SMB variables, document LOCAL_FILES_BASE_PATH | .env |  | Not Started | 1 | Core Refactoring | Environment cleanup
4 | Environment | Create uploads Directory | Ensure backend_webbone/uploads directory exists | backend_webbone/uploads |  | Not Started | 5 |  | Directory structure
4 | Environment | Verify Route Configuration | Check that file routes are properly mounted | backend_webbone/src/app.js |  | Not Started | 1 |  | Route verification
5 | Error Handling | Improve Error Messages | Make all error responses user-friendly | backend_webbone/src/controllers/file.controller.js |  | Not Started | 2 | Function Cleanup | User experience
5 | Error Handling | Add Comprehensive Logging | Add debug logging for all file operations | backend_webbone/src/controllers/file.controller.js |  | Not Started | 2 | Function Cleanup | Development and debugging
5 | Error Handling | Handle Edge Cases | Add proper error handling for disk full, permissions, etc | backend_webbone/src/controllers/file.controller.js |  | Not Started | 3 | Function Cleanup | Production readiness
6 | MVP Verification | Client File Upload Works | Verify clients can upload files to their folder |  |  | Not Started | 1 | Testing | Core MVP requirement
6 | MVP Verification | Client Folder Organization Works | Verify clients can create and manage subfolders |  |  | Not Started | 1 | Testing | Core MVP requirement
6 | MVP Verification | Client File Download Works | Verify clients can download their files |  |  | Not Started | 1 | Testing | Core MVP requirement
6 | MVP Verification | Admin Folder Management Works | Verify admin can see and manage all client folders |  |  | Not Started | 1 | Testing | Admin MVP requirement
6 | MVP Verification | File Operations Work | Verify rename, delete, create folder operations |  |  | Not Started | 1 | Testing | Core MVP requirement
7 | Cleanup | Remove Unused Imports | Remove SMB2 and related unused imports | backend_webbone/src/controllers/file.controller.js | 1-5 | Not Started | 5 | Core Refactoring | Code cleanup
7 | Cleanup | Remove SMB Constants | Remove SMB_SINGLE_UPLOAD_LIMIT and other SMB constants | backend_webbone/src/controllers/file.controller.js | 42 | Not Started | 5 | Core Refactoring | Code cleanup
7 | Cleanup | Update Code Comments | Update comments to reflect local-only storage | backend_webbone/src/controllers/file.controller.js |  | Not Started | 1 | Function Cleanup | Documentation
7 | Cleanup | Remove writeWithTimeout Function | Remove or simplify timeout wrapper (may not be needed for local FS) | backend_webbone/src/controllers/file.controller.js | 200-220 | Not Started | 1 | Function Cleanup | Simplification
8 | Documentation | Update README | Document the simplified file storage system | README.md |  | Not Started | 2 | MVP Verification | Project documentation
8 | Documentation | Document API Endpoints | Create or update API documentation for file operations | docs/ |  | Not Started | 3 | MVP Verification | API documentation
8 | Documentation | Environment Setup Guide | Document environment variables and setup | docs/ |  | Not Started | 1 | Environment | Setup documentation

## Issues_Analysis
Issue Category,Issue Description,Current State,Impact,Recommended Solution,Priority
Architecture,SMB and Local Storage Dual Mode,"File controller supports both SMB and local storage, making code complex and hard to maintain",High,"Remove SMB support entirely, use only local storage",Critical
Architecture,Environment Variable Dependency,"Code heavily depends on CLIENT_FILES_USE_SMB environment variable",Medium,"Hardcode to local storage, remove conditional logic",High
Architecture,Path Handling Inconsistency,"Uses both smbJoin() for SMB paths and path.join() for local paths",Medium,"Standardize on path.join() for local filesystem",High
Security,Path Traversal Vulnerability,"Basic path traversal protection but could be strengthened",High,"Implement robust path validation and sanitization",Critical
Security,No File Type Restrictions,"No validation on uploaded file types",Medium,"Implement file extension whitelist",High
Security,No File Size Limits,"No per-client storage quotas or file size limits",Medium,"Add configurable file size and storage limits",Medium
Performance,Large File Upload Issues,"SMB uploads have 10MB single-request limit, complex resumable upload system",High,"Simplify resumable uploads for local storage only",High
Performance,Timeout Handling,"writeWithTimeout wrapper adds complexity for local filesystem operations",Low,"Remove timeout wrapper for local FS operations",Low
Code Quality,Complex Conditional Logic,"Every file operation has if(USE_SMB) branches",High,"Remove all SMB conditional branches",Critical
Code Quality,Unused SMB Helper Functions,"Multiple SMB helper functions (smbReaddir, smbWriteFile, etc.) taking up space",Medium,"Remove all SMB helper functions",Medium
Code Quality,Mixed Error Handling,"Inconsistent error messages and handling between SMB and local modes",Medium,"Standardize error handling for local storage only",Medium
Functionality,Resumable Upload Complexity,"Resumable upload system is overly complex for local storage",Medium,"Simplify resumable uploads for local filesystem",Medium
Functionality,Admin Folder Management Missing,"No clear admin endpoints for managing client folders",High,"Add dedicated admin endpoints for folder management",High
Functionality,Client Folder Auto-Creation,"Client folders may not be automatically created",Medium,"Ensure client folders are created on user registration",Medium
Dependencies,Unused SMB2 Package,"smb2 package is installed but will not be used in MVP",Low,"Remove smb2 from package.json",Low
Environment,SMB Environment Variables,"Multiple SMB-related environment variables are not needed",Low,"Remove SMB environment variables from .env",Low
Testing,No Automated Tests,"No unit or integration tests for file operations",High,"Add test coverage for core file operations",Medium
Testing,Manual Testing Required,"All functionality needs manual verification",Medium,"Create test scripts or automated test suite",Low
Documentation,Outdated Comments,"Code comments reference SMB functionality",Low,"Update comments to reflect local-only storage",Low
Documentation,Missing API Documentation,"File upload/management API endpoints not documented",Medium,"Create comprehensive API documentation",Low